## Revised Version (As of 0709)
CDG x SMU Project Plan
| PROJECT TITLE | Project CDG |  |  | COMPANY NAME | [10 empty] | Comfort DelGro
| SMU SUPERVISOR | Tan Poh Choo
[5 empty] | AUGUST | [9 empty] | AUGUST - SEPTEMBER | [19 empty] | SEPTEMBER - OCTOBER | [24 empty] | NOVEMBER | [19 empty] | NOVEMBER - DECEMBER
PHASE NUMBER | TASK TITLE | OWNER | START DATE | DUE DATE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16
[5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
[5 empty] | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3
0 | Pre-Phase
0.1 | Research for Initial Scope | ALL | 2021-08-16 | 2021-08-23 | bar: WEEK 1 M 16 to WEEK 2 M 23
0.2 | Initial Finalization of Scope | ALL | 2021-08-23 | 2021-08-27 | bar: WEEK 2 M 23 to WEEK 2 F 27
0.3 | Sign-offs from CDG | Sherms | 2021-08-27 | 2021-08-27 | bar: WEEK 2 F 27
1 | Data Collection
1.1 | Receiving relevant data from CDG | Sherms | 2021-08-16 | 2021-09-01 | bar: WEEK 1 M 16 to WEEK 3 W 1
1.2 | Data Scraping from Social Media and Other Sources | ALL | 2021-08-16 | 2021-08-25 | bar: WEEK 1 M 16 to WEEK 2 W 25
1.3 | Data Compilation | ALL | 2021-08-25 | 2021-08-26 | bar: WEEK 2 W 25 to WEEK 2 T 26
1.4 | Use Case Identification | ALL | 2021-08-26 | 2021-08-27 | bar: WEEK 2 T 26 to WEEK 2 F 27
1.5 | Finalize Scope | ALL | 2021-08-27 | 2021-08-30 | bar: WEEK 2 F 27 to WEEK 3 M 30
1.6 | Preparation for Survey Questionnaire | ALL | 2021-08-27 | 2021-09-01 | bar: WEEK 2 F 27 to WEEK 3 W 1
1.7 | Survey Marketing and Distribution | ALL | 2021-09-01 | 2021-09-30 | bar: WEEK 3 W 1 to WEEK 7 T 30
2 | Infrastructure Setup
2.1 | Azure Authorization | Sherms | 2021-08-16 | 2021-08-20 | bar: WEEK 1 M 16 to WEEK 1 F 20
2.2 | GitHub Setup | Sherms | 2021-08-16 | 2021-08-20 | bar: WEEK 1 M 16 to WEEK 1 F 20
3 | Data Preparation and Pre-processing
3.1 | Review Data | ALL | 2021-08-23 | 2021-08-30 | bar: WEEK 2 M 23 to WEEK 3 M 30
3.2 | Clean and transform data | ALL | 2021-08-25 | 2021-09-01 | bar: WEEK 2 W 25 to WEEK 3 W 1
4 | Exploratory Data Analysis
4.1 | Conduct EDA on scrapped data | ALL | 2021-09-01 | 2021-09-15 | bar: WEEK 3 W 1 to WEEK 5 W 15
4.2 | Conduct EDA on CDG data | ALL | 2021-09-01 | 2021-09-15 | bar: WEEK 3 W 1 to WEEK 5 W 15
4.3 | Conduct EDA on compiled data - Survey | Iris/Sonia | 2021-09-06 | 2021-09-30 | bar: WEEK 4 M 6 to WEEK 7 T 30
4.4 | Check-in From CDG/Confirm on further analysis | Sherms | 2021-09-10 | 2021-09-13 | bar: WEEK 4 F 10 to WEEK 5 M 13
5 | Analysis-1
5.1 | Survey data | Iris | 2021-09-13 | 2021-09-22 | bar: WEEK 5 M 13 to WEEK 6 W 22
5.1.1 | - Clustering Analysis Part 1 | Shaza | 2021-09-13 | 2021-09-22 | bar: WEEK 5 M 13 to WEEK 6 W 22
5.1.2 | - Text Analysis (sentiment) Part 1 | Sonia | 2021-09-13 | 2021-09-24 | bar: WEEK 5 M 13 to WEEK 6 F 24
5.1.3 | - Geospatial analysis | Sherms | 2021-09-20 | 2021-09-22 | bar: WEEK 6 M 20 to WEEK 7 M 27
5.2 | Scrapped Data (reddit) | Ivy | 2021-09-13 | 2021-09-24 | bar: WEEK 5 M 13 to WEEK 6 F 24
5.2.1 | - Text Analysis (Topic Modelling/Sentiment) Part 1 | Ivy | 2021-09-13 | 2021-09-24 | bar: WEEK 5 M 13 to WEEK 6 F 24
5.3 | Factor Analysis | Shaza | 2021-09-23 | 2021-09-27 | bar: WEEK 6 T 23 to WEEK 7 M 27
5.4 | Combine Analysis to generate insights | ALL | 2021-09-20 | 2021-09-24 | bar: WEEK 6 M 20 to WEEK 7 M 27
Milestone 1 | bar: WEEK 6 F 24 to WEEK 7 M 27
6 | Initial Development
6.1 | Skeleton Design for Dashboard | Hx | 2021-09-13 | 2021-09-17 | bar: WEEK 5 M 13 to WEEK 5 F 17
6.2 | Dashboard Development on current initial overview | Hx | 2021-09-16 | 2021-09-28 | bar: WEEK 5 T 16 to WEEK 7 T 28
7 | Mid-Terms
7.1 | Mid-Term Presentation | ALL | 2021-09-23 | 2021-10-04 | WEEK 8 M 4: TRUE
7.2 | Gather Feedback from Mid-Term Presentation | ALL | 2021-10-04 | 2021-10-05 | bar: WEEK 8 M 4 to WEEK 8 T 5
Milestone 2 | bar: WEEK 8 T 5
8 | Analysis-2
8.1 | Survey Data | Iris | 2021-10-06 | 2021-10-20 | bar: WEEK 8 W 6 to WEEK 10 W 20
8.1.1 | Factor Analysis Part 2 | Shaza | 2021-10-06 | 2021-10-20 | bar: WEEK 8 W 6 to WEEK 10 W 20
8.1.2 | Clustering Analysis Part 2 | Shaza | 2021-10-06 | 2021-10-20 | bar: WEEK 8 W 6 to WEEK 10 W 20
8.1.3 | Text Analysis Part 2 (Topic Modelling) | Sonia | 2021-10-06 | 2021-10-20 | bar: WEEK 8 W 6 to WEEK 10 W 20
8.2 | CSISG Data | Ivy | 2021-10-08 | 2021-11-01 | bar: WEEK 8 F 8 to WEEK 12 M 1
8.2.1 | Text Analysis (Sentiment + Topic Modelling) | Sonia | 2021-10-18 | 2021-10-27 | bar: WEEK 10 M 18 to WEEK 11 W 27
8.2.2 | Correlation Analysis | Ivy | 2021-10-21 | 2021-10-29 | bar: WEEK 10 T 21 to WEEK 11 F 29
8.3 | Geospatial Analysis | Sherms | 2021-10-21 | 2021-11-01 | bar: WEEK 10 T 21 to WEEK 12 M 1
8.3.1 | CSISG Data | Sherms | 2021-10-21 | 2021-11-01 | bar: WEEK 10 T 21 to WEEK 12 M 1
8.3.2 | Clustering Results | Sherms | 2021-10-21 | 2021-11-01 | bar: WEEK 10 T 21 to WEEK 12 M 1
8.4 | Combine analysis to generate insights | ALL | 2021-10-21 | 2021-11-05 | bar: WEEK 10 T 21 to WEEK 12 F 5
8.5 | Focus Group Discussion - Car Rental | ALL | 2021-11-08 | 1 Dec 1121 | bar: WEEK 13 M 8 to WEEK 13 F 12
9 | Final Development
9.1 | Dashboard Development | Hx | 2021-10-21 | 2021-11-05 | bar: WEEK 10 T 21 to WEEK 12 F 5
10 | UAT
10.1 | Prepare for UAT testing | Hx | 2021-11-05 | 2021-11-12 | bar: WEEK 13 M 8 to WEEK 13 F 12
10.2 | Execute UAT | Hx | 2021-11-12 | 2021-11-17 | bar: WEEK 13 F 12 to WEEK 14 W 17
10.2 | Gather feedback from UAT testing | Hx | 2021-11-12 | 2021-11-17 | bar: WEEK 13 F 12 to WEEK 14 W 17
10.3 | Amendments from UAT | Hx | 2021-11-17 | 2021-11-19 | bar: WEEK 14 W 17 to WEEK 14 F 19
10.4 | UAT signoff from CDG | Sherms | 2021-11-19 | 2021-11-22 | bar: WEEK 14 F 19 to WEEK 15 M 22
11 | Final Deliverables
11.1 | Final Presentation | Sonia | 2021-11-11 | 2021-11-29 | WEEK 15 W 24: TRUE; WEEK 16 M 29: TRUE
11.2 | Poster | Sherms/Shaza | 2021-11-11 | 2021-11-26 | WEEK 15 F 26: TRUE
11.3 | Video | Iris | 2021-11-10 | 2021-11-26 | WEEK 15 F 26: TRUE
11.4 | Final Report | Sonia | 2021-11-01 | 2021-11-26 | WEEK 15 F 26: TRUE
11.5 | Handover | Sherms | 2021-11-29 | 2021-12-15 | bar: WEEK 16 M 29 to WEEK 16 F 3
11.5.1 | User Guide | Sherms | 2021-11-29 | 2021-12-15 | bar: WEEK 16 M 29 to WEEK 16 F 3
11.5.2 | Dashboard Migration | Sherms | 2021-11-29 | 2021-12-15 | bar: WEEK 16 M 29 to WEEK 16 F 3
Milestone 3 | bar: WEEK 16 F 3
Completed
Ongoing
Over-run
On-Hold
Newly-Added
Milestone
Up-Next (Planned)
To-Be Confirmed

## Initial Version
CDG x SMU Project Plan
| PROJECT TITLE | Project CDG |  |  | COMPANY NAME | [10 empty] | Comfort DelGro
| SMU SUPERVISOR | Tan Poh Choo
[5 empty] | AUGUST | [9 empty] | AUGUST - SEPTEMBER | [19 empty] | SEPTEMBER - OCTOBER | [24 empty] | NOVEMBER | [19 empty] | NOVEMBER - DECEMBER
PHASE NUMBER | TASK TITLE | OWNER | START DATE | DUE DATE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16
[5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
[5 empty] | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3
1 | Data Collection
1.1 | Receiving relevant data from CDG |  | 2021-08-16 | 2021-08-20 | bar: WEEK 1 M 16 to WEEK 1 F 20
1.2 | Data Scraping from Social Media and Other Sources |  | 2021-08-16 | 2021-08-25 | bar: WEEK 1 M 16 to WEEK 2 W 25
1.3 | Data Compilation |  | 2021-08-26 | 2021-08-27 | bar: WEEK 2 T 26 to WEEK 2 F 27
1.4 | Use Case Identification |  | 2021-08-30 | 2021-08-31 | bar: WEEK 3 M 30 to WEEK 3 T 31
1.5 | Finalize Scope |  | 2021-08-31 | 2021-09-01 | bar: WEEK 3 T 31 to WEEK 3 W 1
2 | Infrastructure Setup
2.1 | Azure Authorization |  | 2021-08-16 | 2021-08-20 | bar: WEEK 1 M 16 to WEEK 1 F 20
2.2 | GitHub Setup |  | 2021-08-16 | 2021-08-20 | bar: WEEK 1 M 16 to WEEK 1 F 20
2.3 | Data modelling for Social Media Scrapping |  | 2021-09-01 | 2021-09-06 | bar: WEEK 3 W 1 to WEEK 4 M 6
2.4 | Data modelling for Facebook Analytics |  | 2021-09-01 | 2021-09-06 | bar: WEEK 3 W 1 to WEEK 4 M 6
3 | Data Preparation and Pre-processing
3.1 | Review Data |  | 2021-09-07 | 2021-09-08 | bar: WEEK 4 T 7 to WEEK 4 W 8
3.2 | Clean and transform data |  | 2021-09-08 | 2021-09-13 | bar: WEEK 4 W 8 to WEEK 4 F 10
3.3 | ETL from source systems |  | 2021-09-13 | 2021-09-14 | bar: WEEK 4 F 10 to WEEK 5 M 13
4 | Exploratory Data Analysis
4.1 | Conduct EDA on scrapped data |  | 2021-09-13 | 2021-09-17 | bar: WEEK 5 M 13 to WEEK 5 F 17
4.2 | Conduct EDA on CDG data |  | 2021-09-13 | 2021-09-17 | bar: WEEK 5 M 13 to WEEK 5 F 17
4.3 | Conduct EDA on compiled data |  | 2021-09-13 | 2021-09-17 | bar: WEEK 5 M 13 to WEEK 5 F 17
Milestone 1
5 | Analysis-1
5.1 | Text Analysis |  | 2021-09-17 | 2021-09-20 | bar: WEEK 5 F 17 to WEEK 6 M 20
5.2 | Applying machine learning models |  | 2021-09-20 | 2021-09-22 | bar: WEEK 6 M 20 to WEEK 6 W 22
6 | Initial Development
6.1 | Skeleton Design for Dashboard |  | 2021-09-17 | 2021-09-22 | bar: WEEK 5 F 17 to WEEK 6 W 22
7 | UAT-1
7.1 | Prepare for UAT testing |  | 2021-09-23 | 2021-09-24 | bar: WEEK 6 T 23 to WEEK 6 F 24
7.2 | Execute UAT |  | 2021-09-24 | 2021-09-27 | bar: WEEK 6 F 24 to WEEK 7 M 27
7.3 | Gather feedback from UAT testing |  | 2021-09-27 | 2021-09-29 | bar: WEEK 7 M 27 to WEEK 7 W 29
7.4 | UAT signoff from CDG |  | 2021-09-29 | 2021-10-01 | bar: WEEK 7 W 29 to WEEK 7 F 1
8 | Mid-Terms
8.1 | Mid-Term Presentation |  | 2021-09-27 | 2021-10-06 | bar: WEEK 7 M 27 to WEEK 8 W 6
8.2 | Gather Feedback from Mid-Term Presentation |  | 2021-10-07 | 2021-10-08 | bar: WEEK 8 T 7 to WEEK 8 F 8
Milestone 2 | bar: WEEK 8 F 8
5 | Analysis-2
5.1 | Social Media Analysis |  | 2021-10-11 | 2021-10-15 | bar: WEEK 9 M 11 to WEEK 9 F 15
5.1.1 | Conduct network analysis |  | 2021-10-14 | 2021-10-20 | bar: WEEK 9 T 14 to WEEK 10 W 20
5.2 | Geospatial Analysis |  | 2021-10-11 | 2021-10-15 | bar: WEEK 9 M 11 to WEEK 9 F 15
5.2.1 | Conduct location analysis |  | 2021-10-14 | 2021-10-20 | bar: WEEK 9 T 14 to WEEK 10 W 20
6 | Final Development
6.1 | Dashboard Development |  | 2021-10-18 | 2021-10-27 | bar: WEEK 10 M 18 to WEEK 11 W 27
6.2 | Signoff from CDG |  | 2021-10-27 | 2021-11-01 | bar: WEEK 11 W 27 to WEEK 12 M 1
7 | UAT-2
7.1 | Prepare for UAT testing |  | 2021-10-29 | 2021-11-03 | bar: WEEK 11 F 29 to WEEK 12 W 3
7.2 | Execute UAT |  | 2021-11-03 | 2021-11-05 | bar: WEEK 12 W 3 to WEEK 12 F 5
7.3 | Gather feedback from UAT testing |  | 2021-11-08 | 2021-11-12 | bar: WEEK 13 M 8 to WEEK 13 F 12
7.4 | UAT signoff from CDG |  | 2021-11-12 | 2021-11-17 | bar: WEEK 13 F 12 to WEEK 14 W 17
8 | Final Deliverables
8.1 | Final Presentation |  | 2021-11-15 | 2021-11-24 | bar: WEEK 14 M 15 to WEEK 15 W 24
8.2 | Poster |  | 2021-11-15 | 2021-11-25 | bar: WEEK 14 M 15 to WEEK 15 T 25
8.3 | Video |  | 2021-11-10 | 2021-11-25 | bar: WEEK 13 W 10 to WEEK 15 T 25
8.4 | Final Report |  | 2021-11-01 | 2021-11-25 | bar: WEEK 12 M 1 to WEEK 15 T 25
8.5 | Handover |  | 2021-11-29 | 2021-12-03 | bar: WEEK 16 M 29 to WEEK 16 F 3
Milestone 3 | bar: WEEK 16 F 3
Completed
Ongoing
Milestone
Up-Next (Planned)